## SPRINT
WEEK1
Week #1 (4 days / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 16*1) | D1 | D2 | D3 | D4
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10
|  |  |  | 16 | 11 | 6 | 0 | Ideal Burndown
|  |  | 16 | 16 | 13 | 7 | 0 | Remaining Hrs (Total)
Initial SetUP | Research on Tech Stack | Kesiya | 4 | 4 | 4 | 3 | 0
| Review Documents & Understand project requirements | Kiran | 4 | 4 | 3 | 2 | 0
| Task Allocation | Nancy | 4 | 4 | 3 | 1 | 0
| Scrum set up | Vasudha | 4 | 4 | 3 | 1 | 0
Team:
Kesiya | 4 hours / Week
Kiran | 4 hours / Week
Nancy | 4 hours / Week
Vasudha | 4 hours / Week
Total Available Hours During Sprint 1: | 16
WEEK 2
Week #2 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 24*1) | D1 | D2 | D3 | D4
|  |  |  | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17
|  |  |  | 24 | 15 | 7 | 0 | Ideal Burndown
|  |  | 24 | 24 | 14 | 10 | 0 | Remaining Hrs (Total)
Initial Set Up | Architecture Diagram | Kesiya | 6 | 6 | 3 | 3 | 0
| Create and update the README.md file | Kiran | 6 | 6 | 4 | 2 | 0
DB and AWS initial Set Up | Set Up DB and AWS | Nancy | 6 | 6 | 4 | 3 | 0
Set Up Scrum Schedules | Set Up Scrum Meetings, sheets, etc. | Vasudha | 6 | 6 | 3 | 2 | 0
Team:
Kesiya | 6 hours / Week
Kiran | 6 hours / Week
Nancy | 6 hours / Week
Vasudha | 6 hours / Week
Total Available Hours During Sprint 2: | 24
WEEK 3
Week #3 (4 days / week3)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 32*1) | D1 | D2 | D3 | D4
|  |  |  | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24
|  |  |  | 32 | 21 | 10 | 0 | Ideal Burndown
|  |  | 32 | 32 | 22 | 11 | 0 | Remaining Hrs (Total)
Front End Coding for Components | Initial UI wireframing & Register/Sign-Up UI | Kiran | 8 | 8 | 6 | 3 | 0
| Reservation Page Set Up | Nancy | 8 | 8 | 5 | 2 | 0
| Home Page Set Up | Vasudha | 8 | 8 | 4 | 3 | 0
| Basic Front end set up | Kesiya | 5 | 5 | 4 | 1 | 0
| Scrum Meeting Updates | Kesiya | 3 | 3 | 3 | 2 | 0
Team: | 8 hours / Week
Kesiya | 8 hours / Week
Kiran | 8 hours / Week
Nancy | 8 hours / Week
Vasudha
Total Available Hours During Sprint 3: | 32
WEEK 4
Week #4 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 32*1) | D1 | D2 | D3 | D4
|  |  |  | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31
|  |  |  | 32 | 22 | 12 | 0 | Ideal Burndown
|  |  | 32 | 32 | 25 | 11 | 0 | Remaining Hrs (Total)
Create a Payment through miles miles, User Account Page, Home Page, Login Page, Sign Up page, Cancel Page,Reservation Page | Login UI | Kiran | 5 | 5 | 3 | 1 | 0
| Payment Page Set Up | Vasudha | 5 | 5 | 3 | 2 | 0
| Reservation Page | Nancy | 4 | 4 | 4 | 2 | 0
| Payment through miles page | Kesiya | 4 | 4 | 3 | 1 | 0
| User Account | Kesiya | 4 | 4 | 4 | 2 | 0
| Cancel Page | Nancy | 4 | 4 | 3 | 2 | 0
| Home Page | Vasudha | 3 | 3 | 3 | 1 | 0
| Resolve UI conflicts between login & register components CSS | Kiran | 3 | 3 | 2 | 0 | 0
Team:
Kesiya | 8 hours / Week
Kiran | 8 hours / Week
Nancy | 8 hours / Week
Vasudha | 8 hours / Week
Total Available Hours During Sprint 4: | 32
WEEK 5
Week #5 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 32*1) | D1 | D2 | D3 | D4
|  |  |  | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07
|  |  |  | 32 | 22 | 12 | 0
|  |  | 32 | 32 | 22 | 13 | 0
front end pages for route selection, seat selection , front end for admin | Admin View Bookings page | Nancy | 5 | 5 | 2 | 2 | 0
| Routes UI | Kiran | 4 | 4 | 3 | 1 | 0
| Seat Selection | Vasudha | 4 | 4 | 3 | 2 | 0
| Flight List UI Components | Kiran | 4 | 4 | 3 | 2 | 0
| Seat Pricing | Vasudha | 4 | 4 | 3 | 1 | 0
| Admin account page | Nancy | 3 | 3 | 2 | 2 | 0
Backend Set Up and Mileage Rewards | Backend Set Up | Kesiya | 4 | 4 | 3 | 1 | 0
| Mileage Calculation | Kesiya | 4 | 4 | 3 | 2 | 0
Team:
Kesiya | 8 hours / Week
Kiran | 8 hours / Week
Nancy | 8 hours / Week
Vasudha | 8 hours / Week
Total Available Hours During Sprint 5: | 32
WEEK 6
Week #6 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 32*1) | D1 | D2 | D3 | D4
|  |  |  | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14
|  |  |  | 32 | 22 | 12 | 0
|  |  | 32 | 32 | 21 | 11 | 0
front end pages for Ticket, Admin Flight Updates | Admin Flight Updates Page | Nancy | 5 | 5 | 2 | 2 | 0
| Ticket Page | Vasudha | 3 | 3 | 3 | 1
Backend APIs for login /sign up, seat selection, mileage management, account | API for Login | Kiran | 4 | 4 | 3 | 1 | 0
| API for Seat Selection | Vasudha | 5 | 5 | 3 | 2 | 0
| API for Flight Search and Book Flight | Kiran | 4 | 4 | 2 | 2 | 0
| API for account page | Vasudha | 4 | 4 | 3 | 1 | 0
| API for mileage management | Kesiya | 4 | 4 | 2 | 1 | 0
DB Set Up and Connection with API | DB Set Up with API | Nancy | 3 | 3 | 3 | 1 | 0
Team:
Kesiya | 8 hours / Week
Kiran | 8 hours / Week
Nancy | 8 hours / Week
Vasudha | 8 hours / Week
Total Available Hours During Sprint 6: | 32
WEEK 7
Week #7 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 32*1) | D1 | D2 | D3 | D4
|  |  |  | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21
|  |  |  | 32 | 22 | 12 | 0
|  |  | 32 | 32 | 18 | 12 | 0
Backend for admin pages, flight selection, book flight, Ticket page, view reservations | Admin API | Nancy | 4 | 4 | 2 | 2 | 0
| Login API integration in frontend | Kiran | 4 | 4 | 2 | 1 | 0
| View Reservation API | Kesiya | 8 | 8 | 5 | 3 | 0
| FlightSearch API call integration in RouteSelector component | Kiran | 4 | 4 | 2 | 2 | 0
| Ticket Page API | Vasudha | 6 | 6 | 4 | 2 | 0
Initial Connection with database | DB Set Up | Nancy | 2 | 2 | 0 | 0 | 0
| DB data Population | Nancy, Vasudha | 2,2 | 4 | 3 | 2 | 0
Team:
Kesiya | 8 hours / Week
Kiran | 8 hours / Week
Nancy | 8 hours / Week
Vasudha | 8 hours / Week
Total Available Hours During Sprint 7: | 32
WEEK 8
Week #8 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 32*1) | D1 | D2 | D3 | D4
|  |  |  | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28
|  |  |  | 32 | 22 | 12 | 0
|  |  | 32 | 32 | 17 | 12 | 0
Final Integration of APIs with DB | Component integration with db | Nancy | 5 | 5 | 2 | 2 | 0
| Component integration with db | Kiran | 8 | 8 | 4 | 3 | 0
| Component integration with db | Vasudha | 8 | 8 | 4 | 2 | 0
| Component integration with db | Kesiya | 8 | 8 | 4 | 4 | 0
AWS SET Up | AWS Set Up | Nancy | 3 | 3 | 3 | 1 | 0
Team:
Kesiya | 8 hours / Week
Kiran | 8 hours / Week
Nancy | 8 hours / Week
Vasudha | 8 hours / Week
Total Available Hours During Sprint 8: | 32
WEEK 9
Week #9 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 32*1) | D1 | D2 | D3 | D4
|  |  |  | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14
|  |  |  | 32 | 22 | 12 | 0
|  |  | 32 | 32 | 18 | 13 | 0
Final TESTING | Test own components | Nancy | 8 | 8 | 4 | 3 | 0
| Test own components | Kiran | 8 | 8 | 5 | 3 | 0
| Test own components | Vasudha | 8 | 8 | 4 | 4 | 0
| Test own components | Kesiya | 8 | 8 | 5 | 3 | 0
Team:
Kesiya | 8 hours / Week
Kiran | 8 hours / Week
Nancy | 8 hours / Week
Vasudha | 8 hours / Week
Total Available Hours During Sprint 9: | 32